## Лист1
Task | Start date | Days to complete
Analysis phase | 2020-02-10 | 9
Design the C# application | 2020-02-20 | 3
Design the website | 2020-02-22 | 2
Create the C# application | 2020-02-24 | 10
Create the website | 2020-02-29 | 10
Testing - C# application | 2020-03-07 | 5
Testing - website | 2020-03-10 | 6
Deployment phase | 2020-03-16 | 4